## README
Weekly Compliance Checklist — Template (per Project)
How to use
1. Fill in the Meta sheet first. Required — the parser reads project_key and the period from there, not from the filename.
2. One file = one project. Do not combine multiple projects in one file.
3. Fill Wins, Blockers, Dependencies, and Todos as needed — some may be left empty.
4. Row 2 of each data sheet is an EXAMPLE (gray, italic). Delete it before submitting.
5. Do not leave a blank row in the middle of your data — the parser stops there.
6. Do not change sheet names, column names, or column order. Column names are the database column names.

## Meta
Meta — required
Field | Value | Notes
schema_version | 2 | Do not change. Used by the parser to pick the right mapping.
project_key* | AIRPAY | Jira project key. Must match exactly, uppercase.
project_name | Airpay Reengineering | Project display name. Prefilled from Jira.
team_slug |  | Owning team. Optional — used to group rows on the Compliance Board.
period_type* | weekly | weekly or monthly.
period_start* | 2026-08-03 | Format YYYY-MM-DD.
period_end* | 2026-08-09 | Format YYYY-MM-DD.
submitted_by* | fixtures@linkit360.com | Filler’s email. Must be registered in app_users.
submitted_at |  | Format YYYY-MM-DD. Leave blank — filled automatically on upload.
notes |  | Free-text notes. Optional.
parser_profile | default | Do not change. Selects the column mapping.

## Wins
win_date* | category* | title* | description | jira_issue_key | impact
2026-08-05 | Platform | Payment gateway v2 live | Zero-downtime migration | AIRPAY-482 | Latency -60%
2026-08-06 | DCB | Klickmobi billing fix | Resolved notification bug

## Blockers
title* | priority* | status* | pic* | bottleneck* | next_action* | target_date | jira_issue_key
Sandbox credentials not issued | P1 | In Progress | Andi | Waiting on partner approval | Escalated via PM | 2026-08-12 | AIRPAY-501

## Dependencies
title* | depends_on* | direction* | status* | pic | target_date | jira_issue_key | notes
Needs settlement endpoint | PPOB Developer | outbound | Open | Budi | 2026-08-15 | ARC-77 | Spec sent 2026-07-28

## Todos
title* | pic* | due_date* | priority* | status* | jira_issue_key | notes
Instrument gateway v2 metrics | Andi | 2026-08-14 | P1 | In Progress | AIRPAY-505 | Needed for uptime dashboard
Write postmortem | Rani | 2026-08-16 | P2 | Not Started